# TRANTIATE V2.0 Practitioner Handbook

How to plan, run, govern, assure, and close Trants

| Primary Audience | Transformation leads, enterprise architects, delivery leaders, PMs, product leaders, risk/governance practitioners |
| --- | --- |
| Purpose | Translate the published methodology into repeatable practitioner action. |
| Authority | Companion to the published TRANTIATE White Paper Version 2.0 |

White Paper = methodology authority. Supplementary documents = interpretation and application.

# 1. Practitioner Operating Principle

Introduce once. Define once. Apply many times.

The handbook does not redefine Trantiate. It shows how to use its published constructs consistently. Start with the Target Future, run the complete TRANT lifecycle inside each Trant, assign the four Roles, govern Workers through UWC, govern work through TWO, capture evidence through KEA, and close through TOR.

# 2. Before the First Trant

| Question | Minimum Practitioner Output |
| --- | --- |
| What future are we moving toward? | Target Future representation |
| What current value exists? | VEM findings |
| What gaps separate current from future? | Gap map |
| Which responsibilities are required? | Seer/Maker/Checker/Buyer requirements |
| Which Workers are eligible? | Worker inventory + UWC baseline |
| What work is bounded next? | Initial TWOs |
| What must be evidenced? | Evidence obligations + assurance criteria |
| How will state be seen? | Compass / Snap / Watch setup |

# 3. Running the TRANT Lifecycle

## Target

Clarify the destination and Trant intent.

Confirm Target Future relevance

Define value commitment

Set closure conditions

Identify material policy constraints

## Review

Understand current-state value through VEM.

Extract capabilities, rules, data, dependencies, controls, behaviors

Evaluate future relevance and risk

Disposition to Preserve, Enhance, Retire, or Risk

## Analyze

Identify transformation distance.

Capability gaps

Data/integration gaps

Control/risk gaps

Worker capability/eligibility gaps

## Navigate

Choose the next safe movement.

Sequence work

Resolve dependencies

Set assurance depth

Select Workers

Define HOLD/ESCALATE paths

## Transform

Perform bounded work and generate evidence.

Issue TWOs

Validate UWC

Execute

Capture evidence

Run Checker/Buyer activities

Update KEA/Navigators

# 4. Role Practice

| Role | Practitioner Behaviors | Typical Work Order |
| --- | --- | --- |
| Seer | Protect intent, value, trade-offs, readiness, adoption, and strategic direction. | SWO |
| Maker | Create or transform within scope and return required evidence. | MWO |
| Checker | Verify against quality, architecture, security, risk, data, compliance, control, and other criteria. | CWO |
| Buyer | Evaluate suitability for consumption, operations, user/customer value, or downstream use. | BWO |

# 5. Worker Selection

Use Responsibility First -> Worker Second. Do not design the transformation around whichever agent, vendor, or team happens to be available.

Identify required Role responsibility.

Identify capability needed.

Find eligible Workers.

Validate UWC, access, independence, authority, and autonomy.

Issue the TWO with context and evidence obligations.

Monitor execution and exceptions.

Requalify when material Worker characteristics change.

# 6. UWC and TWO in Practice

UWC governs the Worker. TWO governs the work.

| UWC Answers | TWO Answers |
| --- | --- |
| Who/what is the Worker? | What bounded work is required? |
| What can the Worker do? | Which Trant/TRANT movement does it support? |
| How independently? | What output is expected? |
| What may it access? | What evidence must be returned? |
| What guardrails apply? | What assurance/acceptance conditions apply? |
| When must it hold/escalate? | What constitutes completion? |

# 7. Assurance Practice

Do not let a Worker independently assure its own material output where independence is required.

Do not treat different AI instances as automatically independent if they share model, context, tools, evidence, or assumptions.

Keep conflicting Checker findings visible until policy-defined reconciliation or escalation resolves them.

Distinguish Worker-asserted evidence from independently generated or otherwise verifiable evidence where material.

Treat Buyer acceptance as different from Checker assurance.

# 8. Daily Pulse and Weekly Connect

| Cadence | Purpose | Minimum Content |
| --- | --- | --- |
| Daily Pulse | Operational synchronization | Completed, Next, Blocker, Cross-Impact, Evidence, Exception State |
| Weekly Connect | Cross-Role reconciliation | Target alignment, Checker findings, Buyer feedback, dependencies, Worker conflicts, exceptions, Navigation changes, decisions |

# 9. Closing a Trant

Reconcile TOC intent with actual outcomes.

Confirm Deliverables and incomplete/carryover work.

Review material Worker participation and UWC state.

Review Checker assurance and Buyer acceptance.

Record exceptions and overrides.

Complete TOR.

Create/update Snap.

Assemble TCAP where required.

Decide CONTINUE / REPRIORITIZE / REORIENT / HOLD / COMPLETE.

# 10. Common Failure Modes

| Failure Mode | Practitioner Correction |
| --- | --- |
| Starting with tasks rather than Target Future | Re-establish intent through TOC. |
| Treating AI tool use as Worker governance | Determine whether AI performs substantive Role responsibility; if yes, govern as Worker. |
| Assuming technical access equals permission | Apply Effective Permission. |
| Allowing implicit agent delegation | Require explicit delegated authority and governed delegate Worker. |
| Treating Checker PASS as Buyer acceptance | Run the Buyer responsibility separately. |
| Using dashboards without evidence | Reconnect Navigator state to KEA evidence. |
| Never declaring completion | Use Trant N and explicit closure conditions. |

# 11. Practitioner Exit Criteria

Target Future movement is evidenced.

Material TWOs have traceable status.

Required Workers were governed through applicable UWCs.

Assurance and acceptance conditions are resolved or explicitly carried forward.

Exceptions and overrides are visible.

TOR is complete.

Next movement or completion is explicit.